## Sheet1
[6 empty] | GANTT CHART | [30 empty] | 14 | 12 | 2022
Work Distribution | [5 empty] | SCHEDULE
PA | Task | Team Member | Start Day | Finish Day | Status | 2022-12-14 | 2022-12-15 | 2022-12-16 | 2022-12-17 | 2022-12-18 | 2022-12-19 | 2022-12-20 | 2022-12-21 | 2022-12-22 | 2022-12-23 | 2022-12-24 | 2022-12-25 | 2022-12-26 | 2022-12-27 | 2022-12-28 | 2022-12-29 | 2022-12-30 | 2022-12-31 | 2023-01-01 | 2023-01-02 | 2023-01-03 | 2023-01-04 | 2023-01-05 | 2023-01-06 | 2023-01-07 | 2023-01-08 | 2023-01-09 | 2023-01-10 | 2023-01-11 | 2023-01-12 | 2023-01-13 | 2023-01-14 | 2023-01-15 | 2023-01-16 | 2023-01-17
0 | Role division Requirements analysis | All members | 2022-10-14 | 2022-10-21 | Done
1 | Write Sofware Development Plan | All members | 2022-10-22 | 2022-10-27 | Done
| Survey the demand of customers | Tran Van That Truong Van Hao | 2022-10-26 | 2022-10-26 | Done
| Evaluate the survey's result | All members | 2022-10-26 | 2022-10-27 | Done
| Meeting 2 | Vu Hoang Phuc | 2022-10-27 | 2022-10-27 | Done
| Write Vision Document | All members | 2022-10-28 | 2022-11-02 | Done
| Research UI Design | Trieu Quoc Thai Truong Van Hao | 2022-10-28 | 2022-11-02 | Done
| Assign the specific work to the team member( Front-end or back end) | Vu Hoang Phuc | 2022-11-02 | 2022-11-02 | Done
| Meeting 3 | Vu Hoang Phuc | 2022-11-02 | 2022-11-02 | Done
2 | Revised project plan | All members | 2022-11-03 | 2022-11-16 | Done
| Revised vision document | All members | 2022-11-03 | 2022-11-16 | Done
| Draw Use case Diagram | Trieu Quoc Thai Truong Van Hao | 2022-11-03 | 2022-11-16 | Done
| Write Use-case specification | All members | 2022-11-03 | 2022-11-16 | Done
| Create Gantt Chart | Vu Hoang Phuc | 2022-11-10 | 2022-11-16
| Design simple UI | Trieu Quoc Thai Le Truong Kinh Thanh | 2022-11-10 | 2022-11-16 | Done
| Research about database | Vu Hoang Phuc Tran Van That Truong Van Hao | 2022-11-03 | 2022-11-16 | Done
3,4 | Front End | Trieu Quoc Thai Le Truong Kinh Thanh | 2022-11-17 | 2022-12-14 | Doing
| Home | Trieu Quoc Thai | 2022-11-17 | 2022-11-30 | Doing
| Book view and reader view | Le Truong Kinh Thanh | 2022-11-17 | 2022-11-30 | Doing
| Log in, Sign up | Trieu Quoc Thai Le Truong Kinh Thanh | 2022-11-17 | 2022-11-30 | Doing
| Case Forget password | Trieu Quoc Thai Le Truong Kinh Thanh | 2022-11-17 | 2022-11-30 | Doing
| Reader: Evaluate and Report book | Trieu Quoc Thai Le Truong Kinh Thanh | 2022-11-17 | 2022-11-30 | Doing
| Reader: View history viewed book | Trieu Quoc Thai Le Truong Kinh Thanh | 2022-11-17 | 2022-11-30 | Doing
| Reader: Search book | Trieu Quoc Thai Le Truong Kinh Thanh | 2022-11-17 | 2022-11-30 | Doing
| Reader: Edit profile | Trieu Quoc Thai Le Truong Kinh Thanh | 2022-12-01 | 2022-12-14 | To do
| Admin UI | Trieu Quoc Thai Le Truong Kinh Thanh | 2022-12-01 | 2022-12-14 | To do
| Admin: See the report in the list Delete comments Ban user comment 1 month | Trieu Quoc Thai Le Truong Kinh Thanh | 2022-12-01 | 2022-12-14 | To do
| Admin: adding, editing, deleting,.. Account | Trieu Quoc Thai Le Truong Kinh Thanh | 2022-12-01 | 2022-12-14 | To do
3,4 | Back end | Vu Hoang Phuc Tran Van That Truong Van Hao | 2022-11-17 | 2022-12-14 | Doing
| Create Database | Vu Hoang Phuc Tran Van That Truong Van Hao | 2022-11-17 | 2022-11-30 | Doing
| Save Username and passwword | Vu Hoang Phuc Tran Van That Truong Van Hao | 2022-11-17 | 2022-11-30 | Doing
| Save Username and passwword | Vu Hoang Phuc Tran Van That Truong Van Hao | 2022-11-17 | 2022-11-30 | Doing
| Save Book's Data | Vu Hoang Phuc Tran Van That Truong Van Hao | 2022-12-01 | 2022-12-14 | To do
| Save reader's react (rating, comment) | Vu Hoang Phuc Tran Van That Truong Van Hao | 2022-12-01 | 2022-12-14 | To do
| Save user information | Vu Hoang Phuc Tran Van That Truong Van Hao | 2022-12-01 | 2022-12-14 | To do
| Save history of reader | Vu Hoang Phuc Tran Van That Truong Van Hao | 2022-12-01 | 2022-12-14 | To do
5 | Test | Le Truong Kinh Thanh | 2022-12-15 | 2022-12-23 | To do
| Test report | Le Truong Kinh Thanh | 2022-12-24 | 2022-12-24 | To do
| Fix errors | All members | 2022-12-25 | 2022-12-26 | To do
| Deliver product | All members | 2022-12-28 | 2022-12-28 | To do
Note
To do
Doing
Done